## Project Requirements
f
Project Requirements Form
Project Number | 1 | Project Name | Code Together
Date | 2025-08-28 | Project Manager | Seth Williams, Parker Fletcher, Bryson Dye, Abraham Sharum
Requirement List | [5 empty] | Requirements Analysis
ID | Requirement Description | Requested By | Category | Priority | Acceptance Criteria | Complexity | In Scope? | Test or Verification | Phase or Release
1 | This is an example requirement | Professor Cuevas | Business | P1 - Critical | Good | Medium | No
2 | Search Bar (For Posts) | Seth Williams | Functional | P1 - Critical | It looks good, not clunky, returns relevant posts | High | Yes | Test | On launch
3 | Friends (find, add and delete) | Parker Fletcher | Functional | P2 - High | Be able find/add/remove friends, user friendly | Medium | Yes | button works/ search works | launch
4 | Home Page | Bryson Dye | Interface | P1 - Critical | Easy to navigate, looks nice, usable | High | Yes | Test or Verification | On launch
5 | Account Page | Parker Fletcher | Interface | P1 - Critical | Easy to navigate, looks nice, usable | High | Yes | user can see,use and update home page | launch
6 | Ability to Make Posts | Seth Williams | Functional | P2 - High | Easy to write and submit posts,visually appealing | High | Yes | Test | On launch
7 | Team Code Battle | AB | Non-functional | P3 - Medium | Drive engagment by adding a small competetive game on the side. Promotes working with other users and building relationships online. | High | No | Test | Enhanced experience Phase
8 | Music Playlist (Account Page) | Parker Fletcher | User | P4 - Low | easy useage and works | Medium | No | adding/removing music, playable, and audio works | enhanced experience at latest
9 | Point Shop | Bryson Dye | User | P4 - Low | Some kind of point shop were users can spend the points that they have earned. | Medium | Yes | Test or Verification | Enhanced experience Phase
10 | Search Filter | Seth Williams | Functional | P3 - Medium | Fast and effective, gives relative posts | High | Yes | Test | On launch
11 | #hashtags in posts | Bryson Dye | User | P3 - Medium | Hashtags for posts to categorize them | Medium | Yes | Test or Verification | Enhanced experience Phase
12 | Define Account Info(For Database) | Seth Williams | Data | P1 - Critical | Define all the data a user will have beforehand. | Medium | Yes | Verification | On launch
13 | Save Pictures (Database) | Bryson Dye | Data | P1 - Critical | The ability to save, associate, and display pictures from a database | Medium | Yes | Test or Verification | On launch
14 | Profanity Filter | Seth Williams | Functional | P3 - Medium | Fast and works,need a lexicon and regex (posts) | Low | Yes | Verification | Enhanced experience Phase
15 | Private Messages | Seth Williams | Functional | P2 - High | Easy to access/view, write and send messages. | High | Yes | Verification | Enhanced experience Phase
16 | Built-in IDE for programming | AB | Functional | P3 - Medium | Simple text-editor for programming, could have synatx highlight support | High | No | Test | Enhanced experience Phase
17 | Tutorial Page | Parker Fletcher | Interface | P3 - Medium | Easy to navigate, looks nice, usable, helpful | Medium | Yes | list info for users to have an easier usage of functionality | launch
18 | Website Mascot | Seth Williams | User | P4 - Low | Visually appealing and engaging. Adds fun! | Low | Yes | Verification | Enhanced experience Phase
19 | Account Page(Customization) | Parker Fletcher |  | P3 - Medium | easy for user to update, looks nice | High | Yes | pg can be viewed and update by users | launch
20 | Forgot Password (Account Email) | Bryson Dye | User | P2 - High | Option on log in page that allows for a password reset with email verification. | High | Yes | Test or Verification | Enhanced experience Phase
21 | Moderation | Bryson Dye | Compliance | P2 - High | Moderation tools that allow for post deletion, account suspension, ect. | Medium | Yes | Test or Verification | Enhanced experience Phase
22 | Report Post Button | Bryson Dye | User | P4 - Low | Button successfully reports the post | Medium | Yes | Test or Verification | Enhanced experience Phase
23 | Help Page | Parker Fletcher |  | P3 - Medium | Easy to navigate, looks nice, usable, helpful | Medium | Yes | user can see tips/frequently asked questions | launch
24 | Contact Us Button | Parker Fletcher |  | P3 - Medium | functional | Medium | Yes | user can use button to contact us | launch
25 | Privacy Policy | Parker Fletcher |  | P4 - Low | clear cut and fully transparent | Low | Yes | users can view and understand privacy policy page | launch
26 | Terms of Service | Seth Williams | Compliance | P4 - Low | Clear and precise, not vague. | Low | Yes | Verification | On launch
27 | Date and Time (for Posts) | Parker Fletcher |  | P2 - High | visible area and acurate | Medium | Yes | visiable accurate date/time display | launch
28 | Happy Birthday Message(user's birthday) | Parker Fletcher | User | P4 - Low | functional and accurate | Medium | Yes | bday msg appears on appropriate day of users bday | launch
29 | Notifications | Parker Fletcher |  | P2 - High | real time, functional | Medium | Yes | messages appear and work correctly | launch
30 | Mobile Side Website | Seth Williams | User | P4 - Low | Resizes and fits well, still usable and appealing. | High | No | Verification | Enhanced experience Phase
31 | Weather | Parker Fletcher |  | P4 - Low | accurate forcasting | Medium | Yes | displays weather accuratly for user | enhanced experience
32 | Light and Dark Mode Toggle | Seth Williams | User | P4 - Low | Visually appealing and works for all pages. | High | No | Verification | Enhanced experience Phase
33 | AI/LLM Integration | AB | Non-functional | P4 - Low | Integrate an LLM for possible code assistance and judgment as well as other auxiliary tasks | Medium | No | Test | Enhanced experience Phase
34 | Sounds | AB | Functional | P3 - Medium | Incorporate sounds into the app for an engaging experience | Medium | Yes | Verification | On launch
35 | Setup roles (user,mod, etc) | AB | Functional | P2 - High | Create roles to restrict/provide access to certain users | Medium | Yes | Verification | On launch
36
37
38
39
40

## Terminology Definitions
Field Descriptions
Name | Description
Project Number | Project number is assigned by the project management office (PMO) once the project is approved for funding.
Project Manager | Person responsible for the successful delivery of the project to time costs and quality constraints.
Project Name | Name or title of project.
Requirement ID | Give each requirement a unique ID.
Requirement Description | The feature, function, condition, or capability that is required from the project, product, service, or result.
Requested By | The stakeholder who requested the requirement.
Category | The category or grouping of the requirement (e.g. functional, technical, operational, key performance indicator/result metric, transitional).
Priority | The priority of the requirement (i.e. [1,2,3], [Must have, Should have, Could have, Won’t have], etc.)
Acceptance Criteria | The criteria that the requirement must have for it to be accepted by the project stakeholders.
Complexity | An indication of how complex it will be to deliver the requirement (i.e. [High, Medium, Low, Very Simple, Simple, Hard, etc.])
Test or Verification | How the requirement will be checked and tested (i.e. passes building regulations check)
Phase or Release | The project phase or product release number when the requirement will be delivered.
Categories Descriptions
Name | Description
Business | High-level goals and objectives of the organization.
Stakeholder | Needs and expectations of stakeholders (users, customers, executives, etc.).
Functional | Specific functionality the system must provide.
Non-functional | Quality attributes and system constraints.
Technical | Technology-specific needs like platforms, languages, frameworks.
User | Needs from an end-user perspective, often in the form of user stories.
Interface | Details on how the system will interact with other systems or users.
Data | Requirements around data storage, formats, privacy, and validation.
Security | Authentication, authorization, encryption, and compliance needs.
Regulatory | Legal and regulatory obligations.
Performance | Speed, throughput, load handling.
Availability | Uptime and fault tolerance.
Scalability | Growth handling over time or usage spikes.
Maintainability | Ease of updates, fixes, and enhancements.
Deployment | Specifications for deployment environments or methods.
Training | End-user training, documentation, or support needs.