## Project Requirements
CSCE 40003 Software Engineering
Project Requirements Form
Project Number | 1 | Project Name | Code Together
Date | 2025-08-28 | Project Manager | Seth Williams, Parker Fletcher, Bryson Dye, AB AB
Requirement List | [5 empty] | Requirements Analysis
ID | Requirement Description | Requested By | Category | Priority | Acceptance Criteria | Complexity | In Scope? | Test or Verification | Phase or Release
1 | This is an example requirement | Professor Cuevas | Business | P1 - Critical | Good | Medium | No
2 | Search Bar (For Posts) | Seth Williams | Functional | P1 - Critical | It looks good, not clunky, returns relevant posts | High
3 | Friends (find, add and delete) | Parker Fletcher | Functional | P2 - High | Be able find/add/remove friends, user friendly | Medium
4 | Home Page | Bryson Dye | Interface | P1 - Critical | Easy to navigate, looks nice, usable | High
5 | Account Page | Parker Fletcher | Interface | P1 - Critical | Easy to navigate, looks nice, usable | High
6 | Ability to Make Posts | Seth Williams | Functional | P2 - High |  | High
7 | Team Code Battle | AB | Functional | P3 - Medium |  | High
8 | Music Playlist (Account Page) | Parker Fletcher | User | P4 - Low | easy useage and works | Medium
9 | Point Shop | Bryson Dye | User | P4 - Low |  | Medium
10 | Search Filter | Seth Williams |  | P3 - Medium |  | High
11 | #hashtags in posts | Bryson Dye |  | P3 - Medium |  | Medium
12 | Define Account Info(For Database) | Seth Williams | Data | P1 - Critical |  | Medium
13 | Save Pictures (Database) | Bryson Dye | Data | P1 - Critical |  | Medium
14 | Profanity Filter | Seth Williams |  | P3 - Medium |  | Low
15 | Private Messages | Seth Williams |  | P2 - High |  | High
16 | Built-in IDE for programming | AB |  | P3 - Medium |  | High
17 | Tutorial Page | Parker Fletcher | Interface | P3 - Medium | Easy to navigate, looks nice, usable, helpful | Medium
18 | Website Mascot | Seth Williams | User | P4 - Low |  | Low
19 | Account Page(Customization) | Parker Fletcher |  | P3 - Medium | easy for user to update, looks nice | High
20 | Forgot Password (Account Email) | Bryson Dye |  | P2 - High |  | High
21 | Moderation | Bryson Dye |  | P2 - High |  | Medium
22 | Report Post Button | Bryson Dye |  | P4 - Low |  | Medium
23 | Help Page | Parker Fletcher |  | P3 - Medium | Easy to navigate, looks nice, usable, helpful | Medium
24 | Contact Us Button | Parker Fletcher |  | P3 - Medium | functional | Medium
25 | Privacy Policy | Parker Fletcher |  | P4 - Low | clear cut and fully transparent | Low
26 | Terms of Service | Seth Williams |  | P4 - Low |  | Low
27 | Date and Time (for Posts) | Parker Fletcher |  | P2 - High | visible area and acurate | Medium
28 | Happy Birthday Message(user's birthday) | Parker Fletcher | User | P4 - Low | functional and accurate | Medium
29 | Notifications | Parker Fletcher |  | P2 - High | real time, functional | Medium
30 | Mobile Side Website | Seth Williams |  | P4 - Low |  | High
31 | Weather | Parker Fletcher |  | P4 - Low | accurate forcasting | Medium
32 | Light and Dark Mode Toggle | Seth Williams |  | P4 - Low |  | High
33
34

## Terminology Definitions
Field Descriptions
Name | Description
Project Number | Project number is assigned by the project management office (PMO) once the project is approved for funding.
Project Manager | Person responsible for the successful delivery of the project to time costs and quality constraints.
Project Name | Name or title of project.
Requirement ID | Give each requirement a unique ID.
Requirement Description | The feature, function, condition, or capability that is required from the project, product, service, or result.
Requested By | The stakeholder who requested the requirement.
Category | The category or grouping of the requirement (e.g. functional, technical, operational, key performance indicator/result metric, transitional).
Priority | The priority of the requirement (i.e. [1,2,3], [Must have, Should have, Could have, Won’t have], etc.)
Acceptance Criteria | The criteria that the requirement must have for it to be accepted by the project stakeholders.
Complexity | An indication of how complex it will be to deliver the requirement (i.e. [High, Medium, Low, Very Simple, Simple, Hard, etc.])
Test or Verification | How the requirement will be checked and tested (i.e. passes building regulations check)
Phase or Release | The project phase or product release number when the requirement will be delivered.
Categories Descriptions
Name | Description
Business | High-level goals and objectives of the organization.
Stakeholder | Needs and expectations of stakeholders (users, customers, executives, etc.).
Functional | Specific functionality the system must provide.
Non-functional | Quality attributes and system constraints.
Technical | Technology-specific needs like platforms, languages, frameworks.
User | Needs from an end-user perspective, often in the form of user stories.
Interface | Details on how the system will interact with other systems or users.
Data | Requirements around data storage, formats, privacy, and validation.
Security | Authentication, authorization, encryption, and compliance needs.
Regulatory | Legal and regulatory obligations.
Performance | Speed, throughput, load handling.
Availability | Uptime and fault tolerance.
Scalability | Growth handling over time or usage spikes.
Maintainability | Ease of updates, fixes, and enhancements.
Deployment | Specifications for deployment environments or methods.
Training | End-user training, documentation, or support needs.